## Product Backlog
Product Name: | MICE Manager | [6 empty] | Complete Fields in Green!!!
Team ID: | boilerplate code enemy #1
| Team Member Name | [5 empty] | Initials | Student ID
Required | Jasper Gustafson | [5 empty] | JG | 1001919917
Sprint # | Remaining | Completed This Sprint |  |  |  | Comment
0 | 39 |  |  |  | Total | Total number of features (in column H)
1 | 35 | 4 |  |  | 1 | Total features left at the end of Sprint #1
2 | 35 | 0 |  |  | 2 | Total features left at the end of Sprint #2
3 | 35 | 0 |  |  | 3 | ...and so on
4 | 35 | 0
5 | 35 | 0
6 | 35 | 0
Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
Additional features may be proposed by the student but must be approved by the Product Owner in writing
Sprints
Feature ID | Priority | Required | Bonus Points | Est | Planned | Status | As a... | I want to... | So that I can… | Notes
CF | 1 | 1 |  | 5 | 1 | Finished in Sprint 1 | Manager | Create a new ice cream flavor | Stock and sell dairy products | Base this off of an Item superclass (see design)
MXF | 2 | 1 |  | 1 | 1 | Finished in Sprint 1 | Manager | Create a new “mix in” flavor | Let Customers to add flavors to their ice cream | Base this off of an Item superclass (see design)
MX | 3 | 1 |  | 2 | 1 | Finished in Sprint 1 | Manager | Create a “mix in” request including amount to mix in | Let Customers vary how much mix ins are, uh, mixed in to the ice cream scoop | Include light, normal, extra, and drenched amounts of a mix in (via an enum); cost and price are presumed constant
SCP | 4 | 1 |  | 13 | 1 | Finished in Sprint 1 | Manager | Specify a scoop of ice cream | Mix a flavor of ice cream with mix ins | Include as many mix ins (with amounts of each) as desired; need regression or interactive tests at this point (hence high estimate)
GUI | 5 | 2 |  | 13 |  |  | Manager | Use a GUI instead of a terminal | Reduce training costs | This is the main window, with menu bar, tool bar, text data area, and optionally status bar; list orders in data area
IGUI | 6 | 2 |  | 13 |  |  | Manager | Use dialogs to create items | Reduce training costs | One dialog should server for all items with minor variations
CC | 7 | 2 |  | 5 |  |  | Manager | Create a new container | Stock and sell dairy products | Containers have varying maximum number of scoops permitted; cost and price are assumed to be zero
CS | 8 | 2 |  | 8 |  |  | Server | Create a serving of 1 or more ice cream scoops with mix ins in a container with toppings | Create dairy products to sell | Pick a container, 1-N scoop flavors, and 0-N toppings via one or more dialogs, instance a serving object, and add to array list
LOGO | 9 | 3 |  | 5 |  |  | Customer | Slowly draw stylized logo with vectors as splash screen | Have a more attractive program launch | May use provided vector file or create your own (this gives practice with drawing on a canvas before the exam)
SAVD | 10 | 3 |  | 8 |  |  | Manager | Save all data to a default file | Ensure our data isn’t lost
LALL | 11 | 3 |  | 8 |  |  | Owner | Load data from a specified file | Franchise my company
SALL | 12 | 3 |  | 5 |  |  | Owner | Save all data to a specified file | Franchise my company
CTM | 13 | 4 |  | 3 |  |  | Manager | Create a new server | Staff the emporium
CB | 14 | 4 |  | 2 |  |  | Server | Create a new beloved customer | Keep track of our customers
CO | 15 | 4 |  | 8 |  |  | Server | Create an order of many servings of ice cream | Serve everyone in a customer party
CSB | 16 | 4 |  | 1 |  |  | Customer | Create a serving of ice cream in a container with toppings | Self-order and not have to deal with people | This just enables the Customer role to do what the Server can do in defining a serving…
COB | 17 | 4 |  | 1 |  |  | Customer | Create an order of many servings of ice cream | Self-order and not have to deal with people | ...and order
CE | 18 | 4 |  | 5 |  |  | Manager | Create an emporium that stocks items and maintains a cash register | Manage the emporium | This includes item stocks, server and customer lists, and the cash register
MST | 19 | 5 |  | 8 |  |  | Manager | Manage the state of each order (unfilled -> filled -> paid, or unfilled -> canceled) | Ensure each order is filled and payment collected
POS | 20 | 5 |  | 5 |  |  | Server | Show the servings in an order for the servers (what to prepare) | Know what to put into each serving in an order | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
POC | 21 | 5 |  | 5 |  |  | Customer | Show the servings in an order for the customer (what was ordered / how much it costs) | Verify that my order was taken correctly and see the price | This can simply be text in a MessageDialog, or something snazzier; probably similar to PS
PIX | 22 | 5 |  | 13 |  |  | Customer | Add and display pictures for each item (container, ice cream flavor, and topping) | Better understand the menu | Store path and filename of image for each ice cream and mix in flavor, and display when ordering
CENEW | 23 |  |  | 13 |  |  | Owner | Create a new franchise | Franchise my company
CM | 24 |  |  | 3 |  |  | Owner | Create a new manager | Delegate management tasks to a pro
P&L | 25 |  |  | 8 |  |  | Manager | Add a Profit & Loss statement, showing all income, expenses, and total profit | Ensure that we’re making a profit and thus avoid bankruptcy
RI | 26 |  |  | 5 |  |  | Manager | Display an Inventory Report, listing every item and the quantity in stock | Ensure we don’t run out of any product and thus disappoint our customers
RTM | 27 |  |  | 8 |  |  | Manager | Display a Server Report, listing all info about each server including # of orders served | Better manage our team and reward productive team members
ETMS | 28 |  |  | 8 |  |  | Manager | Change a server salary | Offer promotions and pay bumps to motivate our team members
AI | 29 |  |  | 8 |  |  | Server | Restock items (ice cream flavor, container, and topping) | Ensure we can fill every order
PS | 30 |  |  | 5 |  |  | Customer | Show the components of a serving (container, scoops, and toppings) for verification | Ensure my order was taken correctly | Select serving in dialog (or data area if clever), then use toString method in a dialog to display details
RO | 31 |  |  | 8 |  |  | Manager | Create an Order Report, showing all pending orders (unfilled and filled but unpaid) | Better manage our production process
RB | 32 |  |  | 5 |  |  | Manager | Display a Customer Report, listing all info about each customer | Better attract repeat customers and handle complaints
EF | 33 |  |  | 8 |  |  | Manager | Edit an ice cream flavor | Improve our data and keep it synced to reality
EC | 34 |  |  | 8 |  |  | Manager | Edit a container | Improve our data and keep it synced to reality
ET | 35 |  |  | 8 |  |  | Manager | Edit a new topping | Improve our data and keep it synced to reality
ROA | 36 |  |  | 3 |  |  | Manager | Add Order Report option to show completed as well as pending orders | Review our order history seeking patterns to understand how to improve efficiency and profit
XI | 37 |  |  | 21 |  |  | Manager | Retire an item (no longer enable its selection for a new order, but keep in reports) | Remove items no longer offered from the menu
XT | 38 |  |  | 13 |  |  | Manager | Suspend a server (no longer allow their selection for an order or restock, but keep in reports) | Remove team members who aren’t currently active from our drop-down lists (except reports)
XXT | 39 |  |  | 5 |  |  | Manager | Restore a server | Add a former team member tack into service

## Sprint 01 Backlog
Sprint # | 1 |  | Complete Fields in Green!!!
Start on | 2022-09-27 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-10-04
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 4
Day 1 Left | 4 | 0
Day 2 Left | 4 | 0
Day 3 Left | 4 | 0
Day 4 Left | 4 | 0
Day 5 Left | 4 | 0
Day 6 Left | 4 | 0
Day 7 Left | 0 | 4
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 | CF |  | -Create Item,IceCreamFlavor; super IceCreamFlavor constructor’s arguments to parent class Item | Completed Day 7
2 | MXF |  | -Create MixInFlavor; super constructor’s arguments to parent Item | Completed Day 7
3 | MX |  | -Create MixIn and MixInAmount; MixIn contains both a MixInFlavor and MixInAmount, MixIn.toString() returns those values for use | Completed Day 7
4 | SCP |  | -Create Scoop; contains a MixIn and IceCreamFlavor. .toString() returns flavor with a list of MixIns [can be added via addMixin()]. Regression test for functionality. | Completed Day 7 | MixIn list has an unwanted space preceding it
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 02 Backlog
Sprint # | 2 |  | Complete Fields in Green!!!
Start on | 2022-10-04 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-10-11
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 03 Backlog
Sprint # | 3 |  | Complete Fields in Green!!!
Start on | 2022-10-11 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-10-18
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 04 Backlog
Sprint # | 4 |  | Complete Fields in Green!!!
Start on | 2022-11-08 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-11-15
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 05 Backlog
Sprint # | 5 |  | Complete Fields in Green!!!
Start on | 2022-11-15 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-11-22
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84

## Sprint 06 Backlog
Sprint # | 6 | BONUS | Complete Fields in Green!!!
Start on | 2022-11-29 |  | *** Create a new Sprint Backlog for EVERY SPRINT ***
End on | 2022-12-06
Demo on | TBD
| Remaining | Completed (this day)
Total Tasks | 1
Day 1 Left | 1 | 0
Day 2 Left | 1 | 0
Day 3 Left | 1 | 0
Day 4 Left | 1 | 0
Day 5 Left | 1 | 0
Day 6 Left | 1 | 0
Day 7 Left | 1 | 0
IMPORTANT: This is an optional sprint for students seeking additional points
Task ID | Feature ID | Assigned To | Description | Status | Notes
1 |  |  | --> Add tasks to complete each feature for this sprint
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84